## ISO-NE Asset Condition Mar20
March 2020 ISO-NEW ENGLAND ASSET Condition Update - ISO-NE Public
Primary Driver | Section # | Asset Condition ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Asset Condition Grouping | Description | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Is the project Grandfathered on May 18, 2015 | PPA (I.3.9) Approval | TCA Approval | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs
Asset Condition
Table A
Maine
Asset Condition | 1a | 24 | ME | MEPCO |  |  | 12/2020 |  | Section 396 & 3001 Structure Replacement |  |  |  | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2019-12-10 |  |  |  | 16900000 | 16900000 | 16900000 | 16900000 | 16000000 | 16000000 | 19900000 | 19900000 | 19900000 | 19900000
New Hampshire
Asset Condition | 1a | 86 | NH | New Hampshire Transmission |  |  | 12/2020 | Seabrook 345 kV GIS Switchyard Phase 2 Equipment Replacement Part of Asset Condition #85 | Phase 2 of mulit-phase project involving like for like equipment replacement. Phase 2 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Ward Hill 394 line, and replacing two GIS 345kV Circuit Breakers and related switches that are the 394 line termination equipment. Post-top insulators for the 394 line located in the open-air to GIS transition yard will also be replaced. Phase 2 also includes replacing Breaker Failure Relay Protection Systems for the 394 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Not Applicable | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 87 | NH | New Hampshire Transmission |  |  | 12/2021 | Seabrook 345 kV GIS Switchyard Phase 3 Equipment Replacement Part of Asset Condition #85 | Phase 3 of mulit-phase project involving like for like equipment replacement. Phase 3 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Scobie Pond 363 line, and replacing two GIS 345kV Circuit Breakers and related switches that are the 363 line termination equipment. Post-top insulators located in the open-air to GIS transition yard will also be replaced. Phase 3 also includes replacing Breaker Failure Relay Protection Systems for the 363 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Not Applicable | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 104 | NH | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line L163 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 14000000 | 14000000 | 14000000 | 16992000
Asset Condition | 1a | 105 | NH | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line A152 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 6100000 | 6884000 | 6884000 | 6884000
Asset Condition | 1a | 186 | NH | Eversource |  |  | 12/2021 |  | 345 kV Structure Replacement Projects - Line 326 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 5200000 | 3630000
Asset Condition | 1a | 187 | NH | Eversource |  |  | 09/2020 |  | 345 kV Structure Replacement Projects - Line 367 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 14100000 | 13631000
Asset Condition | 1a | 188 | NH | Eversource |  |  | 11/2020 |  | 345 kV Structure Replacement Projects - Line 373 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 10300000 | 10995000
Asset Condition | 1a | 189 | NH | Eversource |  |  | 11/2020 |  | 345 kV Structure Replacement Projects - Line 379 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 9700000 | 11589000
Asset Condition | 1a | 191 | NH | Eversource |  |  | 12/2020 |  | 345 kV Structure Replacement Projects - Line 385 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 14000000 | 14408000
Asset Condition | 1a | 192 | NH | Eversource |  |  | 12/2020 |  | 345 kV Structure Replacement Projects - Line 391 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 16400000 | 17313000
Vermont
Massachusetts
Asset Condition | 1a | 63 | MA | Eversource |  |  | 06/2023 |  | Lexington Station #320 Asset Condition Upgrade Project | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Not Applicable | NR | No | [6 empty] | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 16612000
Asset Condition | 1a | 28 | MA | Eversource |  |  | 06/2023 |  | 115 kV GIS breaker replacement at Kingston Street #514 Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Not Applicable | No | No |  |  |  | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 39082000
Asset Condition | 1a | 90 | MA | Eversource |  |  | 12/2021 |  | Canal Station #980 BPS and Asset Condition Upgrade Project | [8 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Not Applicable | NR | No | [8 empty] | 17923000 | 17923000 | 17923000 | 17923000 | 17925000
Asset Condition | 1a | 107 | MA | Eversource |  |  | 06/2021 |  | 349X/Y 345 kV Cable Replacement | [9 empty] | Proposed | Proposed | Proposed | Under Construction | Not Applicable | 2019-10-07 | No | [9 empty] | 72400000 | 72400000 | 72400000 | 72430000
Asset Condition | 1a | 168 | CT | Eversource |  |  | 12/2020 |  | 345 kV Structure Replacement Projects - Line 352 | [11 empty] | Proposed | Under Construction | Not Applicable | NR | No | [11 empty] | 12500000 | 12842000
Asset Condition | 1a | 32 | MA | Eversource |  |  | 12/2020 |  | West Medway Substation #446 Asset Condition Upgrade |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2017-12-01 |  |  |  |  | 18900000 | 18900000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000
Asset Condition | 1a | 42 | MA | Eversource |  |  | 12/2020 |  | Brighton #329 115-kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2018-04-17 | [5 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000
Asset Condition | 1a | 43 | MA | Eversource |  |  | 12/2022 |  | K Street #385 115-kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2018-04-17 | [5 empty] | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000
Asset Condition | 1a | 44 | MA | Eversource |  |  | 12/2026 |  | Mystic #250 115-kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2018-04-17 | [5 empty] | 23900000 | 23900000 | 23900000 | 23900000 | 23900000 | 41113000 | 41113000 | 41113000
Asset Condition | 1a | 53 | MA | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 2 | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Not Applicable | NR | No | [6 empty] | 12353000 | 12353000 | 11353000 | 11353000 | 11353000 | 13044000 | 13044000
Asset Condition | 1a | 25 | MA | Taunton Municipal Light Plant |  |  | 11/2020 |  | Cleary 115 kV ring bus asset replacement - replace existing ring bus with new 115 kV switching station on an adjacent site and reconnect lines and transformers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Not Applicable | NR | NR |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 26 | MA | Eversource |  |  | 12/2023 |  | Rebuild Bourne Substation as a breaker and one half scheme |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Not Applicable | 2018-04-30 | No |  |  |  | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 76000000
Asset Condition | 1a | 27 | MA | Eversource |  |  | 12/2022 |  | Kingston Substation #735 Asset Condition Replacement |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Not Applicable | 2018-04-30 | No |  |  |  | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Asset Condition | 1a | 92 | MA | National Grid, USA |  |  | 05/2021 |  | Robinson Avenue Station #102 Asset Condition Upgrades | [8 empty] | Proposed | Planned | Planned | Planned | Planned | Not Applicable | No | No | [8 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 10340000
Asset Condition | 1a | 145 | MA | National Grid, USA |  |  | 06/2023 |  | Carpenter Hill Control House Rebuild | [9 empty] | Planned | Planned | Planned | Planned | Not Applicable | NR | No | [9 empty] | 6860000 | 6860000 | 6860000 | 6860000
Asset Condition | 1a | 146 | MA | National Grid, USA |  |  | 01/2023 |  | 327 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Not Applicable | NR | No | [9 empty] | 60400000 | 60400000 | 60400000 | 60400000
Asset Condition | 1a | 147 | MA | National Grid, USA |  |  | 01/2023 |  | 303 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Under Construction | Not Applicable | NR | No | [9 empty] | 24700000 | 24700000 | 22472000 | 22472000
Asset Condition | 1a | 148 | MA | National Grid, USA |  |  | 01/2023 |  | 3520 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Not Applicable | NR | No | [9 empty] | 6900000 | 6900000 | 5618000 | 5618000
Asset Condition | 1a | 149 | MA | National Grid, USA |  |  | 01/2023 |  | 315 Line Asset Condition Refurbishments - MA Portion | [9 empty] | Planned | Planned | Planned | Planned | Not Applicable | NR | No | [9 empty] | 53500000 | 53500000 | 53500000 | 53500000
Asset Condition | 1a | 64 | MA | Eversource |  |  | 12/2020 |  | Eversource 345 kV Structure Replacement Project - Line 393 | [6 empty] | Proposed | Proposed | Proposed | In-service | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2019-12-16 | [6 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 17190000 | 17190000 | 17190000
Asset Condition | 1a | 65 | MA | Eversource |  |  | 12/2020 |  | Eversource Laminated Structure Replacement Project - Line 1512 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [6 empty] | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 15100000
Asset Condition | 1a | 180 | MA | Eversource |  |  | 12/2021 |  | 345 kV Structure Replacement Projects - Line 3361 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 6300000 | 6300000
Asset Condition | 1a | 181 | MA | Eversource |  |  | 12/2020 |  | 345 kV Structure Replacement Projects - Line 312 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 41300000 | 41300000
Asset Condition | 1a | 184 | MA | Eversource |  |  | 10/2020 |  | 345 kV Structure Replacement Projects - Line 393 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 11000000 | 9842000
Connecticut
Asset Condition | 1a | 164 | CT | Eversource |  |  | 12/2020 |  | 345 kV Structure Replacement Projects - Line 310 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 19900000 | 19740000
Asset Condition | 1a | 166 | CT | Eversource |  |  | 12/2021 |  | 345 kV Structure Replacement Projects - Line 330 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 17126000 | 17126000
Asset Condition | 1a | 167 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 348 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 19400000 | 15110000
Asset Condition | 1a | 170 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 364 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 17300000 | 16355000
Asset Condition | 1a | 172 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 383 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 22200000 | 22083000
Asset Condition | 1a | 173 | CT | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 387 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 18200000 | 18090000
Asset Condition | 1a | 176 | CT | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 11900000 | 11131000
Asset Condition | 1a | 178 | CT | Eversource |  |  | 12/2021 |  | 345 kV Structure Replacement Projects - Line 3754 | [11 empty] | Under Construction | Under Construction | Not Applicable | NR | No | [11 empty] | 8200000 | 8200000
Asset Condition | 1a | 163 | CT | Eversource |  |  | 12/2020 |  | 667 69 kV line rebuild and asset condition project | [10 empty] | Under Construction | Under Construction | Under Construction | Not Applicable | 43671 | No | [10 empty] | 24080000 | 24079000 | 24079000
Asset Condition | 1a | 17 | CT | United Illuminating Company |  |  | 06/2020 |  | East Shore 345 kV circuit switcher replacement project. Replace 345 kV circuit switchers with dead tank breakers |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Not Applicable | 42570 | 2019-10-30 |  |  | 10931000 | 10931000 | 10931000 | 10931000 | 9234000 | 9234000 | 9234000 | 9234000 | 9234000 | 11240000 | 11240000
Asset Condition | 1a | 18 | CT | United Illuminating Company |  |  | 06/2020 | UI Coastal Substation Flood Mitigation Study Project | East Shore - Raising Impacted 115 kV Equipment |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Not Applicable | NR | 2019-10-30 |  |  |  | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000
Asset Condition | 1a | 19 | CT | United Illuminating Company |  |  | 12/2021 | UI Coastal Substation Flood Mitigation Study Project | Congress 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Not Applicable | NR | No |  |  |  | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000
Asset Condition | 1a | 20 | CT | United Illuminating Company |  |  | 03/2022 | UI Coastal Substation Flood Mitigation Study Project | Grand Avenue - Mill River 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Not Applicable | NR | No |  |  |  | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000
Asset Condition | 1a | 21 | CT | United Illuminating Company |  |  | 09/2022 | UI Coastal Substation Flood Mitigation Study Project | Singer 345kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Not Applicable | NR | No |  |  |  | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000
Asset Condition | 1a | 22 | CT | United Illuminating Company |  |  | 12/2022 | UI Coastal Substation Flood Mitigation Study Project | Pequonnock 115kV Substation rebuild with a new substation adjacent to the existing one |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Not Applicable | 2016-12-28 | No |  |  |  | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000
Asset Condition | 1a | 89 | CT | Eversource |  |  | 07/2020 |  | Replacement of Montville 16X Transformer | [7 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Not Applicable | 2018-05-16 | NR | [7 empty] | 6300000 | 6300000 | 6300000 | 4342676 | 4342676 | 4342676
Asset Condition | 1a | 79 | CT | Eversource |  |  | 05/2020 |  | Eversource 345 kV Structure Replacement Project - Line 398 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Not Applicable | NR | 2019-12-16 | [6 empty] | 7800000 | 7800000 | 7800000 | 9594000 | 9594000 | 9594000 | 9594000
Asset Condition | 1a | 70 | CT | Eversource |  |  | 12/2020 |  | Oil Circuit Breaker Replacement Project at the Plumtree Substation | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [6 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 5868000 | 5868000
Asset Condition | 1a | 82 | CT | Eversource |  |  | 12/2020 |  | Eversource Laminated Structure Replacement Project - Line 1505/1607 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [6 empty] | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000
Asset Condition | 1a | 83 | CT | Eversource |  |  | 05/2020 |  | Eversource Laminated Structure Replacement Project - Line 1675/1080 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [6 empty] | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 18132000
Asset Condition | 1a | 120 | CT | Eversource |  |  | 2020-12-01 |  | Eversource 115 kV Structure Replacement Project - Line 1261 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 18300000 | 18300000 | 18300000 | 20352000
Asset Condition | 1a | 124 | CT | Eversource |  |  | 2020-12-01 |  | Eversource 115 kV Structure Replacement Project - Line 1448 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 6900000 | 6926000 | 6928000 | 6928000
Asset Condition | 1a | 126 | CT | Eversource |  |  | 2020-12-01 |  | Eversource 115 kV Structure Replacement Project - Line 1620 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 10000000 | 9993000 | 9993000 | 9993000
Asset Condition | 1a | 127 | CT | Eversource |  |  | 2020-12-01 |  | Eversource 115 kV Structure Replacement Project - Line 1635 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 5700000 | 5764000 | 5608000 | 5608000
Asset Condition | 1a | 129 | CT | Eversource |  |  | 2020-12-01 |  | Eversource 115 kV Structure Replacement Project - Line 1726 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 16300000 | 16272000 | 16272000 | 16272000
Asset Condition | 1a | 134 | CT | Eversource |  |  | 2020-07-01 |  | Eversource 115 kV Structure Replacement Project - Line 1765 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 12300000 | 12300000 | 12300000 | 13122000
Asset Condition | 1a | 144 | CT | Eversource |  |  | 12/2022 |  | Millstone Substation 15G High Creep Insulator Replacement | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 11500000 | 11500000 | 11500000 | 11500000
Asset Condition | 1a | 91 | CT | United Illuminating Company |  |  | 01/2025 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809A-2 Line (Pequonnock-Congress) | [8 empty] | Proposed | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [8 empty] | 376300000 |  | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 151 | CT | United Illuminating Company |  |  | 01/2025 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809B-2 Line (Pequonnock - Congress) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 152 | CT | United Illuminating Company |  |  | 04/2028 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild portion of 1130 Line (Pequonnock - UI Str. B737) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 21493614 | 21493614 | 21493614
Asset Condition | 1a | 153 | CT | United Illuminating Company |  |  | 04/2028 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 1430 Line (Ash Creek - ESE Str. B648) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 71391220 | 71391220 | 71391220
Asset Condition | 1a | 154 | CT | United Illuminating Company |  |  | 2026-08-08 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 91001-1 Line (Pequonnock - Bridgeport Resco) & 91001-2 Line (Bridgeport Resco - Ash Creek) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 51963324 | 51963324 | 51963324
Asset Condition | 1a | 155 | CT | United Illuminating Company |  |  | 05/2028 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005A-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 40124764 | 40124764 | 40124764
Asset Condition | 1a | 156 | CT | United Illuminating Company |  |  | 05/2028 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005B-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 40124764 | 40124764 | 40124764
Asset Condition | 1a | 157 | CT | United Illuminating Company |  |  | 04/2026 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804A Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 28940339 | 28940339 | 28940339
Asset Condition | 1a | 158 | CT | United Illuminating Company |  |  | 04/2026 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804B Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 28940339 | 28940339 | 28940339
Asset Condition | 1a | 159 | CT | United Illuminating Company |  |  | 01/2024 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 14700532 | 14700532 | 14700532
Asset Condition | 1a | 160 | CT | United Illuminating Company |  |  | 01/2024 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 14700532 | 14700532 | 14700532
Asset Condition | 1a | 161 | CT | United Illuminating Company |  |  | 10/2024 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 14544175 | 14544175 | 14544175
Asset Condition | 1a | 162 | CT | United Illuminating Company |  |  | 10/2024 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Not Applicable | 2019-01-28 | No | [10 empty] | 14544175 | 14544175 | 14544175
Asset Condition | 1a | 139 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1772 | [9 empty] | In-service | In-service | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 10000000 | 10000000 | 10328000 | 10328000
Asset Condition | 1a | 119 | CT | Eversource |  |  | 07/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1256 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 12200000 | 12200000 | 9959000 | 9959000
Asset Condition | 1a | 122 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1310 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Not Applicable | NR | No | [9 empty] | 8300000 | 8299000 | 8299000 | 8299000
Rhode Island
Asset Condition | 1a | 150 | RI | National Grid, USA |  |  | 01/2023 |  | 315 Line Asset Condition Refurbishments - RI Portion | [9 empty] | Planned | Planned | Planned | Planned | Not Applicable | NR | No | [9 empty] | 16500000 | 16500000 | 16500000 | 16500000
Table B
Maine
New Hampshire
Asset Condition | 1b | 198 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - B143 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7410000
Asset Condition | 1b | 199 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - C129 | [12 empty] | Proposed |  | NR | No | [12 empty] | 9100000
Asset Condition | 1b | 200 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - F139 | [12 empty] | Proposed |  | NR | No | [12 empty] | 8000000
Asset Condition | 1b | 201 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - G128 | [12 empty] | Proposed |  | NR | No | [12 empty] | 6910000
Asset Condition | 1b | 202 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - K105 | [12 empty] | Proposed |  | NR | No | [12 empty] | 6080000
Asset Condition | 1b | 203 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - K174 | [12 empty] | Proposed |  | NR | No | [12 empty] | 14740000
Asset Condition | 1b | 204 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - L175 | [12 empty] | Proposed |  | NR | No | [12 empty] | 5250000
Asset Condition | 1b | 205 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - M127 | [12 empty] | Proposed |  | NR | No | [12 empty] | 33430000
Asset Condition | 1b | 206 | NH | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - Y138 | [12 empty] | Proposed |  | NR | No | [12 empty] | 8490000
Asset Condition | 1b | 97 | NH | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
Vermont
Asset Condition | 1b | 195 | VT | Vermont Electric Power Company |  |  | 06/2021 |  | Sand Bar Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers, switches | [11 empty] | Proposed | Proposed | Not Applicable | NR | No | [11 empty] | 10600000 | 10600000
Asset Condition | 1b | 196 | VT | Vermont Electric Power Company |  |  | 12/2020 |  | Berlin Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers & switches. Install a second protection system. | [11 empty] | Proposed | Proposed | Not Applicable | No | No | [11 empty] | 5872719 | 5550000
Asset Condition | 1b | 93 | VT | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
Massachusetts
Asset Condition | 1b | 207 | MA | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1161 | [12 empty] | Proposed |  | NR | No | [12 empty] | 17100000
Asset Condition | 1b | 208 | MA | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1421 | [12 empty] | Proposed |  | NR | No | [12 empty] | 15750000
Asset Condition | 1b | 209 | MA | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1512 | [12 empty] | Proposed |  | NR | No | [12 empty] | 10800000
Asset Condition | 1b | 210 | MA | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1394 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7070000
Asset Condition | 1b | 211 | MA | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1858 | [12 empty] | Proposed |  | NR | No | [12 empty] | 11340000
Asset Condition | 1b | 212 | MA | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1976 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7470000
Asset Condition | 1b | 94 | MA | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
Asset Condition | 1b | 95 | MA | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
Asset Condition | 1b | 96 | MA | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
Asset Condition | 1b | 185 | MA | Eversource |  |  | 02/2020 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Proposed | Proposed | Not Applicable | NR | No | [11 empty] | 26000000 | 26175000
Asset Condition | 1b | 194 | MA | Eversource |  |  | 12/2023 |  | 110-510 & 110-511 lines 115 kV HPFF refurbishment | [11 empty] | Proposed | Proposed | Not Applicable | No | No | [11 empty] | 95000000 | 95000000
Connecticut
Asset Condition | 1b | 213 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1000 | [12 empty] | Proposed |  | NR | No | [12 empty] | 12400000
Asset Condition | 1b | 214 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1042 | [12 empty] | Proposed |  | NR | No | [12 empty] | 6080000
Asset Condition | 1b | 215 | CT | Eversource |  |  | 07/2020 |  | 115-kV Wood Pole and Shield Wire Replacement - 1043 | [12 empty] | Proposed |  | NR | No | [12 empty] | 5394000
Asset Condition | 1b | 216 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1080 | [12 empty] | Proposed |  | NR | No | [12 empty] | 24180000
Asset Condition | 1b | 217 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1208 | [12 empty] | Proposed |  | NR | No | [12 empty] | 8960000
Asset Condition | 1b | 218 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1232 | [12 empty] | Proposed |  | NR | No | [12 empty] | 6700000
Asset Condition | 1b | 219 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1256 | [12 empty] | Proposed |  | NR | No | [12 empty] | 10640000
Asset Condition | 1b | 220 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1280 | [12 empty] | Proposed |  | NR | No | [12 empty] | 12000000
Asset Condition | 1b | 221 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1410 | [12 empty] | Proposed |  | NR | No | [12 empty] | 13000000
Asset Condition | 1b | 222 | CT | Eversource |  |  | 2020-06-01 |  | 115-kV Wood Pole Replacement - 1505 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7100000
Asset Condition | 1b | 223 | CT | Eversource |  |  | 2020-12-01 |  | 115-kV Wood Pole Replacement - 1607 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7626000
Asset Condition | 1b | 224 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1618 | [12 empty] | Proposed |  | NR | No | [12 empty] | 9770000
Asset Condition | 1b | 225 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1732 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7900000
Asset Condition | 1b | 226 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1751 | [12 empty] | Proposed |  | NR | No | [12 empty] | 10750000
Asset Condition | 1b | 227 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1756 | [12 empty] | Proposed |  | NR | No | [12 empty] | 15000000
Asset Condition | 1b | 228 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1765 | [12 empty] | Proposed |  | NR | No | [12 empty] | 14700000
Asset Condition | 1b | 229 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole and Shield Wire Replacement - 1766 | [12 empty] | Proposed |  | NR | No | [12 empty] | 16600000
Asset Condition | 1b | 230 | CT | Eversource |  |  | 12/2023 |  | 115-kV Wood Pole Replacement - 1910 | [12 empty] | Proposed |  | NR | No | [12 empty] | 10300000
Asset Condition | 1b | 231 | CT | Eversource |  |  | 05/2020 |  | 115-kV Line Rebuild and Asset Condition Project - Line 1355 | [12 empty] | Proposed |  | NR | No | [12 empty] | 7450000
Asset Condition | 1b | 67 | CT | Eversource |  |  | 06/2021 |  | Manchester Control House Expansion | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Not Applicable | NR | No | [6 empty] | 21400000 | 21400000 | 21400000 | 21400000 | 48322000 | 48322000 | 48322000
Asset Condition | 1b | 130 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1465 | [9 empty] | Proposed | Proposed | Proposed | Proposed | Not Applicable | NR | No | [9 empty] | 7000000 | 7000000 | 7000000 | 7743000
Rhode Island
Asset Condition | 1b | 98 | RI | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
Asset Condition | 1b | 99 | RI | National Grid, USA |  |  | 09/2025 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Not Applicable | NR | No
In-service
Maine
Asset Condition | 1a | 23 | ME | MEPCO |  |  | 06/2019 |  | Section 388 & 3023 Structure Replacement |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | Not Applicable | NR | No |  |  |  | 101600000 | 101600000 | 101600000 | 82400000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000
Vermont
Asset Condition | 1a | 11 | VT | Vermont Electric Power Company |  |  | 12/2018 | Structure Condition Improvement | Replacement of 115 kV, 230 kV and 345 kV structures as part of the VELCO asset maintenance activities addressing our aging and degrading transmission line infrastructure. 100 to 300 structures will be replaced every year based on outage availability |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | Not Applicable | NR | 2017-12-01 |  | 185000000 | 185000000 | 185000000 | 160200000 | 160200000 | 160200000 | 160200000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000
Asset Condition | 1a | 3 | VT | Vermont Electric Power Company |  |  | 05/2017 | Essex STATCOM Refurbishment | Replace Essex STATCOM power electronics and controls | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | No | 2017-08-13 | 27850000 | 27850000 | 27850000 | 27850000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000
New Hampshire
Asset Condition | 1a | 100 | NH | Eversource |  |  | 01/2020 |  | Eversource 115 kV Structure Replacement Project - Line A126 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 8300000 | 8300000 | 8292000 | 8292000
Asset Condition | 1a | 101 | NH | Eversource |  |  | 10/2019 |  | Eversource 115 kV Structure Replacement Project - Line H123 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 6000000 | 6168000 | 6168000 | 6168000
Asset Condition | 1a | 102 | NH | Eversource |  |  | 12/2019 |  | Eversource 115 kV Structure Replacement Project - Line H141 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 7700000 | 7700000 | 9400000 | 9400000
Asset Condition | 1a | 103 | NH | Eversource |  |  | 10/2019 |  | Eversource 115 kV Structure Replacement Project - Line K174 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 8700000 | 8665000 | 8665000 | 8665000
Asset Condition | 1a | 190 | NH | Eversource |  |  | 01/2020 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 8300000 | 6590000
Asset Condition | 1a | 85 | NH | New Hampshire Transmission |  |  | 12/2019 | Seabrook 345 kV GIS Switchyard Like-for Like Equipment Replacement | Phase 1 of mulit-phase project involving like for like equipment replacement. Phase 1 included replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Timberswamp 369 line. Post-top insulators for the 369 line located in the open-air to GIS transition yard were also replaced. A bridge covering the GILs where they go below grade and then resurface upon entering the fenced-in Protected Area where the GIS Switchyard is located was replaced during this phase. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | Not Applicable | NR | 2019-04-21 | [6 empty] | 77017000 | 77017000 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778
Asset Condition | 1a | 52 | NH | Eversource |  |  | 11/2018 | Eversource Energy Autotransformer Replacement Plan | Replace the Littleton TB-41 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | Not Applicable | 2018-01-29 | NR | [5 empty] | 6200000 | 3891000 | 3891000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000
Asset Condition | 1a | 55 | NH | Eversource |  |  | 07/2018 |  | Eversource 345 kV Structure Replacement Project - Line 307 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 12900000 | 12900000 | 12900000 | 12900000 | 11154000 | 11154000 | 11154000
Asset Condition | 1a | 56 | NH | Eversource |  |  | 2018-08-05 |  | Eversource 345 kV Structure Replacement Project - Line 326 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 11702000 | 11702000 | 11702000
Asset Condition | 1a | 57 | NH | Eversource |  |  | 11/2018 |  | Eversource 345 kV Structure Replacement Project - Line 367 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 15800000 | 15800000 | 15800000 | 15800000 | 15235000 | 15235000 | 15235000
Asset Condition | 1a | 58 | NH | Eversource |  |  | 11/2018 |  | Eversource 345 kV Structure Replacement Project - Line 379 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 14453000 | 14453000 | 14453000
Asset Condition | 1a | 59 | NH | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 381 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 13600000 | 13600000 | 13600000 | 13600000 | 16255000 | 16255000 | 16255000
Asset Condition | 1a | 60 | NH | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 391 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 17858000 | 17858000 | 17858000
Asset Condition | 1a | 51 | NH | Eversource |  |  | 07/2018 | Eversource Energy Autotransformer Replacement Plan | Replace the Deerfield TB-14 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | Not Applicable | 2018-01-29 | No | [5 empty] | 7700000 | 4779000 | 4779000 | 5300000 | 5466000 | 5466000 | 5466000 | 5466000
Asset Condition | 1a | 36 | NH | Eversource |  |  | 03/2018 |  | Install two 40 MVAR reactors on the Scobie 115 kV bus, to accommodate the loss of the reactors connected on the 13.8 kV teriary winding of the TB30 transformer |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | 2017-05-24 | 2018-08-24 |  |  |  |  | 5200000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000
Asset Condition | 1a | 5 | NH | New Hampshire Transmission |  |  | 11/2017 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 2 - Remove Breaker 11 and upgrade sections of Bus 1 | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | 2016-02-23 | 2018-09-11 | 4271787 | 4271787 | 4271787 | 11991000 | 11991000 | 11991000 | 11991000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1a | 35 | NH | Eversource |  |  | 06/2017 |  | Scobie Pond TB30 345/115 kV transformer replacement project |  |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | 2017-05-24 | 2018-08-24 |  |  |  |  | 10300000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000
Asset Condition | 1a | 4 | NH | New Hampshire Transmission |  |  | 11/2016 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 1 - Remove Breaker 22, remove Bus 4 and upgrade sections of Bus 2 | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | 2016-02-23 | 2018-09-11 | 5140351 | 5140351 | 5140351 | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0)
Connecticut
Asset Condition | 1a | 197 | CT | United Illuminating Company |  |  | 10/2019 |  | 1130 Line Optical Ground Wire (OPGW) Replacement | [11 empty] | Under Construction | In-service | Not Applicable | NR | 2019-10-30 | [11 empty] | 8170000 | 8170000
Asset Condition | 1a | 171 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 368 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 7300000 | 7077000
Asset Condition | 1a | 175 | CT | Eversource |  |  | 10/2019 |  | 345 kV Structure Replacement Projects - Line 3252 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 7523000 | 7523000
Asset Condition | 1a | 177 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3424 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 7900000 | 7663000
Asset Condition | 1a | 193 | CT | Eversource |  |  | 12/2019 |  | 115 kV Structure Replacement Projects - Line 1470 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 11111000 | 11111000
Asset Condition | 1a | 50 | CT | Eversource |  |  | 2019-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Card 11F-5X autotransformer. Foundation and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | Not Applicable | 2018-05-16 | No | [5 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 3700000 | 3700000 | 3700000
Asset Condition | 1a | 49 | CT | Eversource |  |  | 01/2020 |  | Southern CT Loop Line Structure Replacements - 1655 115-kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [5 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 17100000 | 17100000 | 18545000 | 18545000
Asset Condition | 1a | 137 | CT | Eversource |  |  | 10/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1769 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 8200000 | 8200000 | 8247000 | 8247000
Asset Condition | 1a | 140 | CT | Eversource |  |  | 10/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1783 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 8200000 | 8200000 | 8113000 | 8113000
Asset Condition | 1a | 141 | CT | Eversource |  |  | 10/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1785 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 9000000 | 9000000 | 8968000 | 8968000
Asset Condition | 1b | 165 | CT | Eversource |  |  | 12/2019 |  | 345 kV Structure Replacement Projects - Line 321 | [11 empty] | Proposed | In-service | Not Applicable | NR | No | [11 empty] | 6500000 | 6481000
Asset Condition | 1a | 169 | CT | Eversource |  |  | 2019-08-07 |  | 345 kV Structure Replacement Projects - Line 362 | [11 empty] | In-service | In-service | Not Applicable | NR | No | [11 empty] | 5088000 | 5088000
Asset Condition | 1a | 174 | CT | Eversource |  |  | 07/2019 |  | 345 kV Structure Replacement Projects - Line 3041 | [11 empty] | In-service | In-service | Not Applicable | NR | No | [11 empty] | 9737000 | 9737000
Asset Condition | 1b | 84 | CT | Eversource |  |  | 12/2018 |  | Eversource Laminated Structure Replacement Project - Line 1921 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | Not Applicable | NR | No | [6 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7887000
Asset Condition | 1a | 135 | CT | Eversource |  |  | 06/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1766 | [9 empty] | Proposed | Under Construction | In-service | In-service | Not Applicable | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5426000
Asset Condition | 1a | 115 | CT | Eversource |  |  | 09/2019 |  | 1608 115 kV Line Cable Replacement | [9 empty] | Proposed | Under Construction | In-service | In-service | Not Applicable | 2019-12-19 | No | [9 empty] | 11300000 | 8182000 | 8182000 | 8182000
Asset Condition | 1a | 117 | CT | Eversource |  |  | 05/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1050 | [9 empty] | Proposed | Under Construction | In-service | In-service | Not Applicable | NR | No | [9 empty] | 7300000 | 7230000 | 7230000 | 7230000
Asset Condition | 1a | 47 | CT | Eversource |  |  | 05/2019 |  | Southern CT Loop Line Structure Replacements - 1342 115-kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | Not Applicable | NR | 2019-12-10 | [5 empty] | 30300000 | 30300000 | 30300000 | 30300000 | 27560000 | 27560000 | 27560000 | 27560000
Asset Condition | 1a | 68 | CT | Eversource |  |  | 04/2019 |  | Card-Montville-Tunnel Corridor Asset Condition and OPGW Installation Project | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | Not Applicable | NR | 2018-10-16 | [6 empty] | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000
Asset Condition | 1a | 73 | CT | Eversource |  |  | 11/2018 |  | Eversource 345 kV Structure Replacement Project - Line 330 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 13500000 | 13500000 | 13500000 | 13500000 | 13695000 | 13695000 | 13695000
Asset Condition | 1a | 116 | CT | Eversource |  |  | 01/2019 |  | 1880 115 kV Line Cable Replacement | [9 empty] | Proposed | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 7200000 | 7200000 | 6959000 | 6959000
Asset Condition | 1a | 34 | CT | Eversource |  |  | 12/2018 |  | Devon Control House Modifications |  |  |  |  | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-04-17 |  |  |  |  | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000
Asset Condition | 1a | 69 | CT | Eversource |  |  | 12/2018 |  | Oil Circuit Breaker Replacement Project at the Frost Bridge Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-08-24 | [6 empty] | 7250000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000
Asset Condition | 1a | 71 | CT | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 310 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 16500000 | 16500000 | 16500000 | 14994000 | 14994000 | 14994000 | 14994000
Asset Condition | 1a | 72 | CT | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 321 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 6000000 | 6000000 | 6000000 | 5847000 | 5847000 | 5847000 | 5847000
Asset Condition | 1a | 75 | CT | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 364 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 14300000 | 14300000 | 14300000 | 14220000 | 14220000 | 14220000 | 14220000
Asset Condition | 1a | 76 | CT | Eversource |  |  | 2018-08-05 |  | Eversource 345 kV Structure Replacement Project - Line 371 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 10600000 | 10600000 | 10600000 | 11546000 | 11546000 | 11546000 | 11546000
Asset Condition | 1a | 74 | CT | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 348 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 19393000 | 19393000 | 19393000
Asset Condition | 1a | 77 | CT | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 383 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 15500000 | 15500000 | 15500000 | 13492000 | 13492000 | 13492000 | 13492000
Asset Condition | 1a | 78 | CT | Eversource |  |  | 12/2018 |  | Eversource 345 kV Structure Replacement Project - Line 387 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 13100000 | 13100000 | 13100000 | 13771000 | 13771000 | 13771000 | 13771000
Asset Condition | 1a | 80 | CT | Eversource |  |  | 07/2018 |  | Eversource 345 kV Structure Replacement Project - Line 3041 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 9700000 | 9700000 | 9700000 | 8276000 | 8276000 | 8276000 | 8276000
Asset Condition | 1a | 81 | CT | Eversource |  |  | 09/2018 |  | Eversource 345 kV Structure Replacement Project - Line 3642 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-12-16 | [6 empty] | 9900000 | 9900000 | 9900000 | 10151000 | 10151000 | 10151000 | 10151000
Asset Condition | 1a | 125 | CT | Eversource |  |  | 12/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1565 | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 11500000 | 11500000 | 11500000 | 9095000
Asset Condition | 1a | 131 | CT | Eversource |  |  | 11/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1751 | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 12500000 | 12500000 | 12500000 | Part of Asset Condition #226
Asset Condition | 1a | 133 | CT | Eversource |  |  | 09/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1759 | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 7300000 | 7300000 | 7300000 | 6076000
Asset Condition | 1a | 136 | CT | Eversource |  |  | 04/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1767 | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 5400000 | 5400000 | 5400000 | 5250000
Asset Condition | 1a | 138 | CT | Eversource |  |  | 10/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1770 (the 1770 line has been replaced by the Plumtree to Stony Hill 1268 line and the Stony Hill to Bates Rock 1485 line) | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 16300000 | 16300000 | 16300000 | 8811000
Asset Condition | 1a | 142 | CT | Eversource |  |  | 12/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1768-CT | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 5200000 | 5200000 | 5200000 | 7586000
Asset Condition | 1a | 143 | CT | Eversource |  |  | 12/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1910 | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5780000
Asset Condition | 1a | 48 | CT | Eversource |  |  | 07/2018 |  | Southern CT Loop Line Structure Replacements - 1508 115-kV | [5 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-08-24 | [5 empty] | 16600000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000
Asset Condition | 1a | 46 | CT | Eversource |  |  | 12/2017 |  | Southern CT Loop Line Structure Replacements - 1261/1598 115-kV | [5 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-04-17 | [5 empty] | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000
Asset Condition | 1a | 33 | CT | Eversource |  |  | 06/2017 |  | 1410 and 100 Line Structure Replacements |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2017-12-01 |  |  |  |  | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000
Asset Condition | 1a | 39 | CT | Eversource |  |  | 11/2017 |  | 3419 line (portion in Connecticut) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-01-02 |  |  |  |  | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38
Asset Condition | 1a | 29 | CT | Eversource |  |  | 09/2017 |  | 1620/1975 line structure replacement |  |  |  | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2017-12-01 |  |  |  | 15500000 | 12500000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 13050000
Asset Condition | 1a | 30 | CT | Eversource |  |  | 12/2016 |  | 3424 line Asset Condition and Storm Hardening |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-01-03 |  |  |  | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000
Asset Condition | 1a | 16 | CT | Eversource |  |  | 06/2016 |  | 3419 line (portion in Connecticut) asset condition and storm hardening. Asset conditon - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-01-03 |  |  | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1
Asset Condition | 1a | 6 | CT | Eversource |  |  | 09/2014 |  | 1570 line clearance remediation. Devon S/S to Beacon Falls S/S. 31 conductor span locations were found to have NESC clearance discrepancies. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2016-12-16 | 6500000 | 6500000 | 6500000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000
Massachusetts
Asset Condition | 1a | 108 | MA | Eversource |  |  | 10/2019 |  | Eversource 115 kV Structure Replacement Project - Line 65-508 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 19500000 | 19500000 | 19500000 | 14043000
Asset Condition | 1a | 112 | MA | Eversource |  |  | 12/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1962 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 20300000 | 4400000 | 4400000 | 4400000
Asset Condition | 1a | 114 | MA | Eversource |  |  | 11/2019 |  | Eversource 115 kV Structure Replacement Project - Line F132 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [9 empty] | 11000000 | 11000000 | 11000000 | 14772000
Asset Condition | 1a | 179 | MA | Eversource |  |  | 10/2019 |  | 345 kV Structure Replacement Projects - Line 336 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 6600000 | 6021000
Asset Condition | 1a | 182 | MA | Eversource |  |  | 11/2019 |  | 345 kV Structure Replacement Projects - Line 354 | [11 empty] | Under Construction | In-service | Not Applicable | NR | No | [11 empty] | 29600000 | 20900000
Asset Condition | 1b | 183 | MA | Eversource |  |  | 09/2019 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Proposed | In-service | Not Applicable | NR | No | [11 empty] | 12500000 | 12358000
Asset Condition | 1a | 88 | MA | National Grid, USA |  |  | 12/2019 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | Not Applicable | NR | No | [6 empty] | 1384000 | 1384000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000
Asset Condition | 1a | 66 | MA | Eversource |  |  | 05/2019 |  | Eversource Laminated Structure Replacement Project - Line 1211/1161 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | Not Applicable | NR | No | [6 empty] | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12598500 | 12985000
Asset Condition | 1a | 109 | MA | Eversource |  |  | 03/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1327 | [9 empty] | Proposed | Under Construction | In-service | In-service | Not Applicable | NR | NR | [9 empty] | 7800000 | 7800000 | 3774000 | 3774000
Asset Condition | 1a | 110 | MA | Eversource |  |  | 03/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1428 | [9 empty] | Proposed | Under Construction | In-service | In-service | Not Applicable | NR | No | [9 empty] | 12100000 | 12100000 | 12100000 | 7487000
Asset Condition | 1a | 15 | MA | Eversource |  |  | 05/2019 |  | Install a new Medway control house which is to be built to BPS standards in a location within the existing station footprint. |  |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | Not Applicable | 2016-01-26 | 2017-07-17 |  |  | 11800000 | 11800000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000
Asset Condition | 1a | 37 | MA | Eversource |  |  | 11/2018 |  | New Mt. Tom protection system control house |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-10-16 |  |  |  |  | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 6657000 | 6657000 | 6657000 | 6657000
Asset Condition | 1a | 62 | MA | Eversource |  |  | 12/2018 |  | Oil Circuit Breaker Replacement Project at the Agawam Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Not Applicable | NR | NR | [6 empty] | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 111 | MA | Eversource |  |  | 12/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1447 | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | NR | [9 empty] | 6600000 | 6600000 | 6600000 | 4332000
Asset Condition | 1a | 113 | MA | Eversource |  |  | 12/2018 |  | Eversource 115 kV Structure Replacement Project - Line 1768-MA | [9 empty] | In-service | In-service | In-service | In-service | Not Applicable | NR | No | [9 empty] | 3000000 | 3000000 | 3000000 | Part of Asset Condition #142
Asset Condition | 1a | 45 | MA | Eversource |  |  | 07/2018 |  | 345-kV 354 Line Structure Replacements | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-10-16 | [5 empty] | 10148000 | 10148000 | 7017000 | 7017000 | 10148000 | 10148000 | 10148000 | 10148000
Asset Condition | 1a | 40 | MA | National Grid, USA |  | 1 | 05/2018 |  | Salem Harbor Substation - 115 kV oil circuit breaker replacements |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | NR |  |  |  |  | 6000000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000
Asset Condition | 1a | 61 | MA | Eversource |  |  | 09/2017 |  | 1231/1242 Structure Replacement Project | [6 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2019-02-15 | [6 empty] | 7966000 | 7966000 | 7966000 | 10860000 | 10860000 | 10860000 | 10860000
Asset Condition | 1a | 38 | MA | Eversource |  |  | 12/2017 |  | 3419 line (portion in Massachusetts) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-01-03 |  |  |  |  | 13700000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000
Asset Condition | 1a | 41 | MA | Eversource |  |  | 06/2013 |  | Scotia Street Substation Project | [5 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2017-07-17 | [5 empty] | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000
Asset Condition | 1a | 12 | MA | Eversource |  |  | 07/2017 |  | Doreen-Oswald Jct. 1211 115 kV Line Structure Replacement |  | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-01-03 |  | 14800000 | 14800000 | 14800000 | 11500000 | 11500000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000
Asset Condition | 1a | 31 | MA | Eversource |  |  | 05/2016 |  | 345 kV GIS breaker replacements at Kingston Street #514 |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2018-05-11 |  |  |  | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000
Asset Condition | 1a | 13 | MA | Eversource |  |  | 01/2017 |  | Ludlow-Thorndike-Palmer (WMA portion) of the X176 115 KV Line Rebuild |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2016-12-16 |  | 14900000 | 8928000 | 8928000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Asset Condition | 1a | 2 | MA | National Grid, USA |  |  | 10/2016 | Crystal Lake Substation Upgrades | Crystal Lake Substation Upgrades | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | 2016-05-05 | 2018-10-10 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000
Asset Condition | 1a | 1 | MA | Eversource |  |  | 06/2016 |  | 3419 line (portion in Massachusetts) asset condition and storm hardening. Asset condition - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 01/03/2018 | 14500000 | 14500000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000
Asset Condition | 1a | 14 | MA | Eversource |  |  | 12/2015 |  | 1231/1242 Line Clearance remediation Project |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2016-12-16 |  |  | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000
Asset Condition | 1a | 7 | MA | Eversource |  |  | 12/2015 |  | 115 kV line 136 Falmouth Tap - West Barnstable Complete structure replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2015-11-25 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000
Asset Condition | 1a | 8 | MA | Eversource |  |  | 05/2015 |  | 381 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2015-11-25 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000
Asset Condition | 1a | 9 | MA | Eversource |  |  | 12/2015 |  | 354 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2015-11-25 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000
Asset Condition | 1a | 10 | MA | Eversource |  |  | 07/2014 |  | 312 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Not Applicable | NR | 2015-11-25 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000
Rhode Island
Asset Condition | 1a | 54 | RI | National Grid, USA |  |  | 12/2019 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | Not Applicable | NR | No | [6 empty] | 427000 | 427000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000
CANCELLED PROJECTS
Asset Condition | 1b | 106 | NH | Eversource |  |  | 12/2023 |  | Eversource 115 kV Structure Replacement Project - Line X178 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Not Applicable | NR | No | [9 empty] | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1b | 118 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1191 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Not Applicable | NR | No | [9 empty] | 8300000 | 8300000 | 8300000 | 8300000
Asset Condition | 1b | 121 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1280 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Not Applicable | NR | No | [9 empty] | 7500000 | 7500000 | 7500000 | 7500000
Asset Condition | 1b | 123 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1410 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Not Applicable | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1b | 132 | CT | Eversource |  |  | 12/2020 |  | Eversource 115 kV Structure Replacement Project - Line 1756 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Not Applicable | NR | No | [9 empty] | 7000000 | 7000000 | 7000000 | Part of Asset Condition #227
Asset Condition | 1a | 128 | CT | Eversource |  |  | 12/2019 |  | Eversource 115 kV Structure Replacement Project - Line 1675 | [9 empty] | Proposed | Under Construction | Cancelleed | Cancelleed | Not Applicable | NR | No | [9 empty] | 7300000 | 7300000 | 7300000 | 7300000
Notes:
1 The original cost for Asset Condition project #40 was above the $5 million threshold. The current project is close to the threshold so this project will remain on the list.
Grandfathered projects on May 18, 2015 are not applicable to the Asset Condition list
Asset Condition List - Status Definitions:
The Section #'s designate the "need" category of the project. Original categories are not changed when a project is placed In-service or Cancelled
Sections - These projects are Asset Condition Upgrades
1a: Planned or Under construction
1b: Concept or Proposed
Concept - Project is under consideration to address an asset condition issue that have be presented to PAC or TOPAC. Costs are not provided
Proposed - Asset owner has determined that the solution is appropriate to address the asset condition issue and the solution has been presented to the P A C. Costs must be provided
Planned - PPA has been approved, if needed. Costs must be provided
Under Construction - Implementation of project is underway Costs must be provided
In-service - Project is in-service. Costs must be provided
Description of PAC interaction and inclusion on the Asset Condition list:
1. If the asset condition issue is on PTF and the PTF cost is greater than $5M, a presentation will be made to the PAC and the project will be added to the Asset Condition list.
2. If the asset condition issue is on the PTF and non-PTF, a presentation will be made to the TOPAC and if the cost of the PTF portion is greater than $5M, a presentation will be made to the PAC and the project will be added to the Asset Condition list.
3. If the asset condition issue is only on the non-PTF, but the corrective action results in changes to the PTF, a presentation will be made to the TOPAC and the project will be added to the Asset Condition list. There is no requirement to discuss the project with the PAC.